## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 |  | choose the data file with atleast 2 crypto currencies | MUST HAVE |  |  | 3- Completed
1 | 1 |  | store thedata in the databases | MUST HAVE |  |  | 3- Completed
1 | 1 |  | calculate the metrics for the data and store the data in the frame | SHOULD HAVE |  |  | 3- Completed
1 | 1 |  | apply parallel tasks concepts to the above steps | MUST HAVE |  |  | 3- Completed
2 | 2 |  | Assign weights for the portfolio.check if weights are assigned based on the rule.calculateportfolio return and risk | MUST HAVE | 1 |  | 3- Completed
2 | 2 |  | create two tables for portfolio and portfolio_assets to store currencies, weights, returns, risks, metrics | SHOULD HAVE | 1 |  | 3- Completed
2 | 2 |  | do the parallel execution run equal-weight,risk-based, performance-based(Thread pool). Save outputs into database. | MUST HAVE |  |  | 3- Completed
2 | 2 |  | Compare portfolio return vs single asset return with some sample data and plot the graphs,draw some insights.Export to CSV | MUST HAVE | 1 |  | 3- Completed
3 | 3 |  | Implement 6 rules to identify risk and store them in the database.Send mail alert if anyone rules fails | SHOULD HAVE | 1 |  | 3- Completed
3 | 3 |  | predict both portfolio and individual returns using linear regression model | SHOULD HAVE | 2 |  | 3- Completed
4 | 4 |  | Implement rule setter and calculate portfolio returns, store in database | MUST HAVE | 1 |  | 3- Completed
4 | 4 |  | Apply stress tests and see how portfolio returns behave | SHOULD HAVE |  |  | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US1 | 1 | Develop a system to collect historical cryptocurrency data for Bitcoin, Ethereum, and XRP from CSV files | Aug 19 | Aug 22 |  | Data Collection | Completed 3 | 4
US1 | 2 | Clean and format the collected cryptocurrency datasets to remove missing values and standardize date formats | Aug 23 | Aug 27 |  | Data Cleaning | Completed 3 | 3
US1 | 3 | Store the cleaned and formatted datasets into a SQLite database to ensure consistent access and integration | Aug 28 | Aug 29 |  | Database Setup | Completed 3 | 3
US2 | 4 | Calculate the daily returns for each cryptocurrency to analyze the percentage change in their value over time | Sep 2 | Sep 4 |  | Return Calculation | Completed 3 | 2
US2 | 5 | Compute the volatility of each cryptocurrency asset to measure the risk and fluctuations in their returns | Sep 5 | Sep 9 |  | Risk Analysis | Completed 3 | 3
US2 | 6 | Calculate the average returns of all cryptocurrencies to summarize their overall performance | Sep 10 | Sep 16 |  | Performance Metrics | Completed 3 | 2
US3 | 7 | Develop a Linear Regression model to predict the future returns of each cryptocurrency based on historical data | Sep 17 | Sep 20 |  | Predictive Modelling | Completed 2 | 2
US3 | 8 | Evaluate the accuracy of the Linear Regression model using metrics such as MSE, MAE, and R² | Sep 21 | Sep 28 |  | Model Evaluation | Completed 2 | 4
US4 | 9 | Implement Equal-weight and Risk-parity portfolio allocation rules to distribute investments based on equal weights and risk-based weighting | Sep 29 | Sep 31 |  | Portfolio Optimization | Completed 2 | 2
US4 | 10 | Implement Sharpe-maximization and Momentum-based allocation rules to optimize portfolio returns based on risk-adjusted performance and recent trends | Oct 1 | Oct 2 |  | Portfolio Optimization | Completed 2 | 4
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
1 |  | Begin collecting cryptocurrency data | Loaded Bitcoin,Ethereum,XRP CSV files
1 |  | Start Cleaning Dataset and formatting | Remove missing values,standardized data formats
1 |  | Prepare database for data Storage | Stored cleaned datasets into SQLite
2 |  | Begin calculating daily Returns | Computed daily returns for all assets
2 |  | Start risk Analysis | Calculated volatility and standard deviation of each assets
2 |  | Compute performance metrics | Calculated average returns and summarized metrics
3 |  | Begin predictive modelling | Applied Linear regression to predict asset returns
3 |  | Evaluate model predictions | Calculate MSE, MAE, and R square for regression accuracy
4 |  | Start portfolio optimization rules | Implemented Equal-weight and risk parity allocation rules
4 |  | Complete portfolio optimization | Applied sharpe-maximization and momentum rules,compared rules

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2019-08-01 | 2023-08-01 |  | Load crypto CSV data | Manual CSV edits | Daily standups | Data Loaded
2 | 2 | 2024-08-01 | 2029-08-01 |  | Clean and store data in SQLite | Multiple file copies | Reusable scripts | Data cleaned
3 | 3 | 2002-09-01 | 2005-09-01 |  | Build predictive model | Raw price checks | Dataset versioning | Model training
4 | 4 | 2006-09-01 | 2008-09-01 |  | Explore data for dashboard | One-off plots | Model evaluation | EDA completed
5 | 5 | 2009-09-01 | 2016-09-01 |  | Build dashboard UI | static CSV reports | Rule testing | Dashboard started
6 | 6 | 2017-09-01 | 2028-09-01 |  | Apply equal weight rule | Manual allocations | Testing with CSVs | Rule done
7 | 7 | 2029-09-01 | 2002-10-01 |  | Apply risk-parity,sharpe,momentum&final testing | Isolated scripts | Code reviews | All rules & integration Done